## Project Schedule Template
Transportation Alternatives Construction Project Schedule
PROJECT SPONSOR:
PROJECT TITLE:
DIRECTIONS: For TA applications involving construction, enter the number of months in the "Estimated Time" column for the below project development tasks or milestones and color the cells in the project schedule timeline. Add any relevant notes in the text boxes below the schedule to provide background on work completed to date (such as design), or to provide context explaining any unique circumstances impacting the estimated length of time for a particular task or phase.
# | TASK / MILESTONE | Estimated Time (Months) | Responsible Entity | FY 2027 |  |  | FY 2028 | [12 empty] | FY 2029 | [11 empty] | FY 2030
|  |  |  | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | DEADLINE FOR PROJECT SPONSORS TO EXECUTE AGREEMENTS WITH TxDOT (JUNE 2028) | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | DEADLINE FOR PROJECT SPONSORS TO RECEIVE AN FPAA AND OBLIGATE FUNDS (AUGUST 2030)
PROJECT INITIATION
Notes: Local Governments (LG) are responsible for submitting the TIP modification to NCTCOG and contacting TxDOT to execute an agreement.
1 | Project Selection (Approval by RTC) | N/A | RTC
2 | Anticipated Deadline to Add Project to NCTCOG TIP (July 23, 2027) | 1 | LG
3 | Anticipated STIP Approval (by November 2027) | 4 | -
4 | Local Government Risk Assessment (Completed after the TIP is approved in November 2027) | 3 | LG/TxDOT
5 | Project Kick-Off Meeting with TxDOT | 1 | LG/TxDOT
6 | Execute Project Agreement | 8 | LG/TxDOT
PRELIMINARY ENGINEERING AND DESIGN
Notes: TxDOT Districts have different requirements related to reviewing design phase work. Consult with TxDOT staff on District-specific expectations.
7 | Consultant Selection Process (if applicable) |  | LG
8 | Submit Schematics (if applicable) |  | LG
9 | Submit 30% Plans for Review |  | LG
10 | TxDOT Review of 30% Plans | 1 | TxDOT
11 | Submit 60% Plans for Review |  | LG
12 | TxDOT Review of 60% Plans | 1 | TxDOT
13 | Submit 95% Plans for Review |  | LG
14 | TxDOT Review of 95% Plans | 1 | TxDOT
15 | Submit PS&E (100% Plans) and Bid Documents for Approval (Cannot be submitted for review until after executing an AFA with TxDOT) |  | LG
16 | PS&E Review and Approval | 1 | TxDOT
ENVIRONMENTAL COMPLIANCE
Notes: All bicycle/pedestrian projects require some degree of environmental compliance documentation. Environmental compliance phase work can only be completed after Design.
17 | Complete TxDOT's Scope Development Tool (Submit at or before Task #9) |  | LG
18 | Resource Agency Review | 1 | TxDOT
19 | Environmental Approval (Submit at least 6 months before desired let date) | 6 | TxDOT
RIGHT OF WAY AND UTILITIES
Notes: Right of Way and Utilities are not eligible activities for TA funds, but are included in this schedule to identify any necessary phase work.
20 | Relocate Incidental Franchise Utilities (if applicable) |  | LG
CONSTRUCTION
Notes: To obligate funds for construction, the opening of bids must occur before the end of August 31, 2030.
21 | Letter of Authority (FPAA and SLOA) | 2 | TxDOT
22 | Project Advertisement (minimum 21 days) | 1 | LG
23 | Open Bids |  | LG
Notes:
An unrealistic project schedule requiring a TIP modification adds four to five months to the project schedule, potentially causing TA funds to lapse.
Additional project tasks or milestones can be added to the project schedule if necessary.
Additional Project Phase Details:
In the boxes below, elaborate on details related to each phase of work completed on the project to date (such as design), or to provide context explaining any unique circumstances impacting the estimated length of time for a particular task or phase. (limited to 500 characters including spaces per box)
PROJECT INITIATION |  |  | PRELIMINARY ENGINEERING AND DESIGN | [10 empty] | ENVIRONMENTAL COMPLIANCE |  |  |  | FY 2029 MAY: RIGHT OF WAY AND UTILITIES; FY 2030 JAN: CONSTRUCTION
Work completed prior to STIP approval and execution of an AFA with TxDOT is not eligible for reimbursement.