## Project Schedule Template
Transportation Alternatives Safe Routes to School Planning Schedule
PROJECT SPONSOR:
PROJECT TITLE:
DIRECTIONS: For TA projects involving Safe Routes to School planning, enter the number of months in the "Estimated Time" column for the below planning development tasks or milestones and color the cells in the project schedule timeline. Add any relevant notes in the text boxes below the schedule to provide background on work completed to date, or to provide context explaining any unique circumstances impacting the estimated length of time for a particular task or phase.
# | TASK / MILESTONE | Estimated Time (Months) | Responsible Entity | FY 2025 |  |  |  | FY 2026 | [12 empty] | FY 2027 | [11 empty] | FY 2028
|  |  |  | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | DEADLINE FOR PROJECT SPONSORS TO EXECUTE AGREEMENTS WITH TxDOT (MAY 2026) | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
PROJECT INITIATION
Notes: Local Governments (LG) are responsible for submitting the TIP modification to NCTCOG and contacting TxDOT to execute an agreement.
1 | Project Selection (Approval by RTC) | N/A | RTC
2 | Anticipated Deadline to Add Project to NCTCOG TIP (June 27, 2025) | 1 | LG
3 | Anticipated STIP Approval (by November 2025) | 6 | -
4 | Local Government Risk Assessment (Completed after the TIP is approved in November 2025) | 3 | LG/TxDOT
5 | Project Kick-Off Meeting with TxDOT | 1 | LG/TxDOT
6 | Execute Project Agreement | 8 | LG/TxDOT
EXISTING CONDITIONS REVIEW
STAKEHOLDER/COMMUNITY ENGAGEMENT
IDENTIFICATION OF ISSUES TO ADDRESS
RECOMMENDATIONS DEVELOPMENT
PLAN DOCUMENT DEVELOPMENT
Notes:
An unrealistic project schedule requiring a TIP modification adds four to five months to the project schedule, potentially causing TA funds to lapse.
Additional planning subtasks or milestones can be added to the project schedule if necessary.
Additional Project Phase Details:
In the boxes below, elaborate on details related to each phase of planning work completed to date (if any), or to provide context explaining any unique circumstances impacting the estimated length of time for a particular task or phase. (limited to 500 characters including spaces per box)
PROJECT INITIATION |  |  | EXISTING CONDITIONS REVIEW | [6 empty] | STAKEHOLDER/COMMUNITY ENGAGEMENT | [7 empty] | AUG: IDENTIFICATION OF ISSUES TO ADDRESS; FY 2027 JUN: RECOMMENDATIONS DEVELOPMENT; FY 2028 MAR: PLAN DOCUMENT DEVELOPMENT
Work completed prior to STIP approval and execution of an AFA with TxDOT is not eligible for reimbursement.